## Risk Register
Technology Risk Assessment (Reputation / Financial / IP loss) — NIST / ISO 27005 / FAIR
Risk ID | Asset / system | STRIDE category | Threat / risk event | Threat source / actor | Vulnerability / cause | Consequence | Risk owner | L | Reputation Impact | Financial Impact | IP Loss Impact | Aggregate Impact | Inherent Score | Inherent Level | Acceptability | Existing controls | Additional control / mitigation | Control type | CVE / SBOM / ref | L' | Rep' | Fin' | IP' | Agg Impact' | Residual Score | Residual Level | Residual Acceptability | Primary loss type | Status
TECH-001 | Customer database / web app | Information disclosure | Customer data breach (PII) | External attacker | Exploited web vulnerability; no WAF | Regulatory fines + churn + brand damage | CISO | 3 | 5 | 4 | 2 | 5 | 15 | High | Reduce (ALARP) | TLS in transit; basic logging | WAF + encryption at rest + IR plan + quarterly pen-test | Protective measure | CVE-2024-XXXX; SBOM-3.1 | 2 | 3 | 3 | 2 | 3 | 6 | Medium | Acceptable w/ review | Reputation | Monitor
TECH-002 | Source-code repository | IP theft | Source-code / trade-secret theft | Malicious insider | Weak access controls; no DLP | Loss of competitive advantage; IP erosion | CTO | 2 | 3 | 3 | 5 | 5 | 10 | High | Reduce (ALARP) | SSO; repo permissions | DLP + least-privilege + repo access monitoring + NDAs | Detective control | SBOM-3.1 | 1 | 2 | 2 | 3 | 3 | 3 | Low | Acceptable | IP | Monitor
TECH-003 | Production SaaS platform | Denial of service | Critical SaaS outage | External / botnet | Single-region dependency; no failover | SLA penalties + revenue loss + reputation | VP Engineering | 3 | 4 | 4 | 1 | 4 | 12 | High | Reduce (ALARP) | CDN; autoscaling | Multi-region HA + DR runbook + chaos testing | Inherently secure design | DR-PLAN-2 | 2 | 3 | 3 | 1 | 3 | 6 | Medium | Acceptable w/ review | Reputation | Monitor
TECH-004 | Software supply chain | Supply chain | Open-source licence / IP infringement | Third-party dependency | Unvetted copyleft dependency | Forced disclosure of proprietary code; litigation | Legal + Eng | 3 | 2 | 3 | 4 | 4 | 12 | High | Reduce (ALARP) | Manual review | SBOM + automated licence scanning in CI + approval gate | Procedural control | SBOM-3.1; SCA-7 | 1 | 1 | 2 | 2 | 2 | 2 | Low | Acceptable | IP | Monitor

## Scales
Scoring Scales & Risk Acceptability
LIKELIHOOD (L) |  |  |  | ACCEPTABILITY (Score = L x AggImpact, 1-25) | [5 empty] | Thresholds used by formulas (do not move):
[10 empty] | Intolerable >= | 16
1 | Rare | Not expected in 5 yrs |  | 16 | Intolerable | Unacceptable - must reduce risk before proceeding |  |  |  | High >= | 10
2 | Unlikely | Once in 2-5 yrs |  | 10 | High | Undesirable - reduce as far as possible (ALARP); justify residual |  |  |  | Medium >= | 5
3 | Possible | Once a year |  | 5 | Medium | Acceptable with review / documented controls
4 | Likely | Several times a year |  | 1 | Low | Broadly acceptable - no further action required
5 | Almost certain | Monthly or more
IMPACT (1-5) per loss dimension |  |  |  | RISK MATRIX (cell = Impa x Like)
|  |  |  | Impact\Likelihood | 1 | 2 | 3 | 4 | 5
1 | No external notice | < $50k | No proprietary exposure | 5 | 5 | 10 | 15 | 20 | 25
2 | Local complaints | $50k-$500k | Minor / non-core IP exposed | 4 | 4 | 8 | 12 | 16 | 20
3 | Negative press / social | $500k-$5M | Some trade secrets at risk | 3 | 3 | 6 | 9 | 12 | 15
4 | National media / churn | $5M-$50M | Core IP / source code exposed | 2 | 2 | 4 | 6 | 8 | 10
5 | Brand crisis, lasting | > $50M | Critical IP lost / patents void | 1 | 1 | 2 | 3 | 4 | 5
Aggregate Impact = MAX(Reputation, Financial, IP). Risk Score = Likelihood x Aggregate Impact.

## Threat Catalog
Threat Catalog — STRIDE / NIST / FAIR (mapped to loss types)
STRIDE category | Threat | Example attack | Affected asset | Typical control | Mapped loss types
Spoofing | Identity spoofing | Credential phishing / token theft | Authentication system | MFA + anomaly detection | Reputation, Financial
Tampering | Data / parameter tampering | Modify therapy or config in transit | Device / API | Input validation + signed payloads | Financial, IP
Repudiation | Action repudiation | Missing or alterable audit logs | Logging system | Tamper-evident logging | Financial
Information disclosure | Data breach | PII / PHI exfiltration | Customer database | Encryption at rest + DLP | Reputation, Financial
Denial of service | Service outage | Volumetric DDoS / resource exhaustion | SaaS platform | Rate limiting + multi-region HA | Financial, Reputation
Elevation of privilege | Privilege escalation | Exploit + lateral movement | Servers / cloud accounts | Least privilege + patching | Financial, IP
Supply chain | Dependency compromise | Malicious or copyleft dependency | Build pipeline | SBOM + licence scan + SLSA provenance | IP, Financial
IP theft | Trade-secret exfiltration | Insider copies source code | Source-code repository | Access monitoring + DLP + NDA | IP